## WIP Schedule
Acme Construction LLC
Work-in-Progress Schedule
As of March 31, 2026
Prepared by 1404 Labs
Job Number | Project Name | Client Name | Project Manager | Original Contract Price | Approved Change Orders | Revised Contract Price | Estimated Total Cost | Costs Incurred to Date | Cost to Complete | % Complete (Cost) | Earned Revenue | Billings to Date | Over/(Under) Billing | Gross Profit to Date | Est. Gross Profit at Compl. | Est. Gross Margin % | Committed Costs (Open POs) | Projected Total Cost | Start Date | Expected Completion | Retainage Held
ACM-2025-018 | Riverside Medical Office Build-Out | Riverside Health Partners | Mike Torres | 2450000 | 185000 |  | 2137500 | 1412750 |  |  |  | 1580000 |  |  |  |  | 310000 |  | 06/15/2025 | 08/30/2026 | 79000
ACM-2025-022 | Downtown Loft Conversion — Phase 2 | Metro Development Group | Sarah Chen | 1875000 | 62000 |  | 1789000 | 1685400 |  |  |  | 1410000 |  |  |  |  | 45000 |  | 03/01/2025 | 05/15/2026 | 70500
ACM-2025-031 | Westfield Elementary School Addition | Westfield School District | Mike Torres | 4200000 | 315000 |  | 3890000 | 1478200 |  |  |  | 2350000 |  |  |  |  | 1250000 |  | 09/01/2025 | 12/15/2026 | 94500
ACM-2026-003 | Harbor Point Retail Shell — Unit 4B | Harbor Point Partners LLC | Sarah Chen | 680000 | -15000 |  | 725000 | 498300 |  |  |  | 395000 |  |  |  |  | 95000 |  | 01/10/2026 | 06/30/2026 | 19750
ACM-2025-014 | Oakdale Fire Station Renovation | Township of Oakdale | Jake Rivera | 1150000 | 48000 |  | 1032000 | 998500 |  |  |  | 1125000 |  |  |  |  | 12000 |  | 02/15/2025 | 04/30/2026 | 56250
ACM-2026-007 | Greenfield Corporate HQ Fit-Out | Greenfield Logistics Inc | Sarah Chen | 3100000 | 0 |  | 2685000 | 342100 |  |  |  | 620000 |  |  |  |  | 890000 |  | 02/01/2026 | 01/15/2027 | 31000
ACM-2025-027 | Summit Brewing Warehouse Expansion | Summit Brewing Co | Jake Rivera | 920000 | 73000 |  | 864000 | 831200 |  |  |  | 945000 |  |  |  |  | 8500 |  | 05/01/2025 | 04/15/2026 | 49700
TOTALS
SUMMARY
Total Overbillings (liability)
Total Underbillings (asset)
Net Over/(Under) Billing Position
Total Earned Revenue
Total Billings to Date
Billing Variance
Weighted Average Gross Margin
Number of Active Projects
Number of Loss Jobs
Total Loss Exposure

## Prior Period
Prior Period Comparison
Prior month data for trend analysis. Paste or link prior WIP here.
# | Project Name | Client | PM | Original Contract | Approved COs | Revised Contract | Est. Total Cost | Costs to Date | Billings to Date | % Complete | Earned Revenue | Over/(Under) Billing | Est. Gross Profit | Est. Gross Margin %
1 | Harbor Point Retail Shell | Harbor Dev LLC | R. Chen | 665000 | -15000 | 650000 | 720000 | 520000 | 480000
2 | Westfield Elementary Addition | USD 501 | M. Torres | 2150000 | 95000 | 2245000 | 1920000 | 1100000 | 1200000
3 | Oakdale Fire Station #7 | City of Oakdale | S. Patel | 4500000 | 180000 | 4680000 | 4100000 | 3700000 | 3800000
4 | Summit Brewing Taproom | Summit Brewing Co | J. Kim | 890000 | 42000 | 932000 | 815000 | 700000 | 750000
5 | Downtown Loft Conversion | Metro Living LLC | A. Nowak | 1875000 | 0 | 1875000 | 1680000 | 1400000 | 1350000
6 | Riverside Medical Office | Riverside Health | R. Chen | 3200000 | 125000 | 3325000 | 2950000 | 1400000 | 1500000
7 | Lincoln Ave Retail Fit-Out | Lincoln Props | M. Torres | 425000 | 0 | 425000 | 390000 | 100000 | 80000

## Change Log
WIP Change Log
Track all changes to project estimates, contract values, and completion percentages.
Date | Job # | Project Name | Field Changed | Old Value | New Value | Changed By | Reason
2026-03-31 | 2026-003 | Oakdale Fire Station #7 | Estimated Total Cost | $4,000,000 | $4,100,000 | S. Patel | Structural steel cost increase
2026-03-31 | 2026-001 | Harbor Point Retail Shell | Approved Change Orders | $0 | -$15,000 | R. Chen | Owner-directed scope reduction
2026-03-28 | 2026-005 | Downtown Loft Conversion | % Complete (PM est.) | 88% | 94.2% | A. Nowak | Drywall and MEP ahead of schedule
2026-03-25 | 2026-004 | Summit Brewing Taproom | Approved Change Orders | $25,000 | $42,000 | J. Kim | Added patio drainage system
2026-03-20 | 2026-006 | Riverside Medical Office | Estimated Total Cost | $2,850,000 | $2,950,000 | R. Chen | HVAC spec change per owner