## Draw Summary
DRAW REQUEST PACKAGE
PROJECT INFORMATION
Project Name | The Madison at Riverside
Property Address | 2400 Riverside Drive, Detroit, MI 48207
Borrower | Riverside Development Partners LLC
Lender | First National Construction Lending
Loan Number | CL-2025-0847
General Contractor | Riverside Builders Inc
Architect | Hamilton Design Associates
DRAW INFORMATION
Draw Number | 7
Draw Date | 2026-04-01
Draw Period | 2026-03-01 to 2026-03-31
FINANCIAL SUMMARY
Total Budget (Contract Sum to Date)
Prior Draws (Previous Certificates)
Current Draw Request
Cumulative Funded
Remaining Balance
Total Retainage Held
BORROWER CERTIFICATIONS
1. | All work for which payment is requested has been completed in accordance with the contract documents.
2. | All amounts previously paid have been applied to costs of the work as indicated.
3. | Current payment requested is now due under the terms of the loan agreement.
4. | No liens, claims, or encumbrances exist against the property except as previously disclosed.
5. | All subcontractors and suppliers have been paid from prior draws as required.
6. | The work is proceeding on schedule and within budget, or variances have been disclosed.
Prepared By: | 1404 Labs
Date: | 2026-04-01
Borrower Signature: | ____________________________

## G702
APPLICATION AND CERTIFICATE FOR PAYMENT
(AIA Document G702)
1. ORIGINAL CONTRACT SUM | 38500000
2. Net Change by Change Orders
3. CONTRACT SUM TO DATE (Line 1 + Line 2)
4. TOTAL COMPLETED & STORED TO DATE
5a. Retainage on Completed Work (10%)
5b. Retainage on Stored Materials (10%)
5c. Total Retainage (5a + 5b)
6. TOTAL EARNED LESS RETAINAGE (Line 4 - Line 5c)
7. LESS PREVIOUS CERTIFICATES FOR PAYMENT | 17842500
8. CURRENT PAYMENT DUE (Line 6 - Line 7)
9. BALANCE TO FINISH INCLUDING RETAINAGE (Line 3 - Line 6)
Retainage Percentage | 10%

## G703
A Item No. | B Description of Work | C Scheduled Value | D Work Completed Previous | E Work Completed This Period | F Materials Stored | G Total Completed & Stored | H % Complete | I Balance to Finish
HARD COSTS
02000 | Site Work & Earthwork | 2850000 | 2850000 | 0 | 0
03000 | Concrete & Foundations | 5200000 | 5200000 | 0 | 0
05000 | Structural Steel & Metals | 4100000 | 3690000 | 410000 | 0
06000 | Rough Carpentry & Framing | 3800000 | 2280000 | 570000 | 190000
07000 | Thermal & Moisture Protection | 2200000 | 880000 | 440000 | 110000
08000 | Doors, Windows & Glazing | 2600000 | 520000 | 390000 | 260000
09000 | Finishes (Drywall, Paint, Flooring, Tile) | 4500000 | 450000 | 675000 | 225000
15000 | Mechanical / HVAC | 3400000 | 1360000 | 510000 | 170000
15500 | Plumbing | 2100000 | 1050000 | 315000 | 0
16000 | Electrical | 2800000 | 1120000 | 420000 | 140000
23000 | Fire Protection | 950000 | 285000 | 142500 | 0
32000 | Exterior Improvements & Landscaping | 1200000 | 0 | 0 | 0
SOFT COSTS
S-01 | Architecture & Engineering | 1800000 | 1620000 | 90000 | 0
S-02 | Permits & Impact Fees | 950000 | 950000 | 0 | 0
S-03 | Legal & Title | 350000 | 280000 | 35000 | 0
S-04 | Builder's Risk Insurance | 425000 | 297500 | 42500 | 0
FINANCING COSTS
F-01 | Loan Origination & Fees | 575000 | 575000 | 0 | 0
F-02 | Capitalized Interest | 1700000 | 1020000 | 121500 | 0
HARD COSTS SUBTOTAL
SOFT COSTS SUBTOTAL
FINANCING COSTS SUBTOTAL
GRAND TOTAL

## Change Order Log
CO # | Date Submitted | Date Approved | Description | Cost Impact (Add/Deduct) | Net Impact (Running) | Schedule Impact (Days) | Status
1 | 2025-09-15 | 2025-09-28 | Upgraded elevator cab finishes per owner request | 185000 |  | 0 | approved
2 | 2025-11-02 | 2025-11-18 | Rock removal — unforeseen subsurface conditions at Building C | 342000 |  | 12 | approved
3 | 2026-01-20 | 2026-02-05 | Structural steel reinforcement per revised wind load calcs | 128000 |  | 5 | approved
TOTALS

## Budget Summary
Line Item | Original Budget | Approved COs | Current Budget | Prior Draws | Current Draw | Total Funded | Remaining | Projected Final Cost | Variance
HARD COSTS
Site Work & Earthwork | 2850000 | 0 |  | 2850000 | 0
Concrete & Foundations | 5200000 | 0 |  | 5200000 | 0
Structural Steel & Metals | 4100000 | 0 |  | 3690000 | 410000
Rough Carpentry & Framing | 3800000 | 0 |  | 2280000 | 760000
Thermal & Moisture Protection | 2200000 | 0 |  | 880000 | 550000
Doors, Windows & Glazing | 2600000 | 0 |  | 520000 | 650000
Finishes (Drywall, Paint, Flooring, Tile) | 4500000 | 0 |  | 450000 | 900000
Mechanical / HVAC | 3400000 | 0 |  | 1360000 | 680000
Plumbing | 2100000 | 0 |  | 1050000 | 315000
Electrical | 2800000 | 0 |  | 1120000 | 560000
Fire Protection | 950000 | 0 |  | 285000 | 142500
Exterior Improvements & Landscaping | 1200000 | 0 |  | 0 | 0
SOFT COSTS
Architecture & Engineering | 1800000 | 0 |  | 1620000 | 90000
Permits & Impact Fees | 950000 | 0 |  | 950000 | 0
Legal & Title | 350000 | 0 |  | 280000 | 35000
Builder's Risk Insurance | 425000 | 0 |  | 297500 | 42500
FINANCING COSTS
Loan Origination & Fees | 575000 | 0 |  | 575000 | 0
Capitalized Interest | 1700000 | 0 |  | 1020000 | 121500
HARD COSTS SUBTOTAL
SOFT COSTS SUBTOTAL
FINANCING COSTS SUBTOTAL
TOTAL PROJECT BUDGET

## Lien Waiver Tracker
Company Name | Trade | Contract Amount | Paid to Date | Due This Draw | Balance | Conditional Progress | Unconditional Progress | Signature Date | Notes
Great Lakes Excavating | Site Work | 2850000 | 2565000 | 0 |  | N/A | Received | 2026-03-05 | Complete — final waiver pending retainage release
Motor City Concrete | Concrete | 5200000 | 4680000 | 0 |  | N/A | Received | 2026-03-08 | Complete
Ironworkers Local 25 Steel | Structural Steel | 4100000 | 3321000 | 369000 |  | Received | Received | 2026-03-28
Midwest Framing Corp | Rough Carpentry | 3800000 | 2052000 | 684000 |  | Received | Received | 2026-03-27
Barrier Systems Inc | Waterproofing & Insulation | 2200000 | 792000 | 495000 |  | Received | Pending | 2026-03-29 | Unconditional for Draw 6 still pending
Wolverine Glass & Glazing | Windows & Glazing | 2600000 | 468000 | 585000 |  | Received | Received | 2026-03-30
Elite Interior Finishes | Finishes | 4500000 | 405000 | 810000 |  | Pending | Received |  | Conditional waiver requested — awaiting return
Comfort Mechanical | HVAC | 3400000 | 1224000 | 612000 |  | Received | Received | 2026-03-26
Allied Plumbing Services | Plumbing | 2100000 | 945000 | 283500 |  | Received | Received | 2026-03-25
PowerLine Electric | Electrical | 2800000 | 1008000 | 504000 |  | Received | Missing | 2026-03-28 | Unconditional for Draw 6 missing — follow up
FireGuard Sprinkler | Fire Protection | 950000 | 256500 | 128250 |  | Received | Received | 2026-03-24
GreenScape Landscaping | Landscaping | 1200000 | 0 | 0 |  | N/A | N/A |  | Not yet mobilized
TOTALS
COMPLIANCE SUMMARY
Active Subcontractors
Conditional Waivers — Received
Conditional Waivers — Pending
Conditional Waivers — Missing
Unconditional Waivers — Received
Unconditional Waivers — Pending/Missing
Conditional Compliance %
Unconditional Compliance %