## G702
AIA DOCUMENT G702 — APPLICATION AND CERTIFICATE FOR PAYMENT
TO OWNER: Riverton Office Park LLC |  | PROJECT: Riverton Office Park — HVAC & Plumbing
PO Box 8840, Detroit MI 48226 |  | 2100 Riverton Blvd, Suite 300, Detroit MI 48226
FROM CONTRACTOR: Apex Mechanical Corp |  | VIA ARCHITECT: Harmon Design Group
7200 Industrial Pkwy, Dearborn MI 48126 |  | 455 W Fort St, Suite 600, Detroit MI 48226
APPLICATION NO: 4 |  | PERIOD TO: March 31, 2026
PROJECT NO: MEC-2025-042 |  | APPLICATION DATE: April 1, 2026
CONTRACTOR'S APPLICATION FOR PAYMENT |  | SUMMARY METRICS
1. ORIGINAL CONTRACT SUM | 1680000 | Contract Sum to Date
2. Net Change by Change Orders | 124500 | Total Completed & Stored
3. CONTRACT SUM TO DATE (Line 1 + 2) |  | % Complete (Overall)
4. TOTAL COMPLETED & STORED TO DATE |  | Total Retainage Held
(Column G on G703, as % of Line 3) |  | Previous Certificates
5. RETAINAGE: |  | Current Payment Due
a. 10% of Completed Work (D+E on G703) |  | Balance to Finish
b. 0% of Stored Material (F on G703) |  | Application Number | 4
c. Total Retainage (Lines 5a + 5b)
6. TOTAL EARNED LESS RETAINAGE (Line 4 - 5c)
7. LESS PREVIOUS CERTIFICATES FOR PAYMENT | 612845
8. CURRENT PAYMENT DUE (Line 6 - 7)
9. BALANCE TO FINISH, INCL. RETAINAGE (Line 3 - 4)

## G703
AIA DOCUMENT G703 — CONTINUATION SHEET
Project: Riverton Office Park — HVAC & Plumbing |  |  |  |  | Application No: 4 Period To: March 31, 2026
Project No: MEC-2025-042 |  |  |  |  | Architect: Harmon Design Group
Contractor: Apex Mechanical Corp
Item No. | Description of Work | Scheduled Value | Work Completed From Previous Application | Work Completed This Period | Materials Presently Stored | Total Completed & Stored To Date | % Complete | Balance To Finish | Retainage
1 | General Conditions / Project Management | 84000 | 63000 | 7000 | 0
2 | Demolition & Removal of Existing Systems | 52000 | 52000 | 0 | 0
3 | Ductwork — Supply & Return | 218000 | 174400 | 32700 | 0
4 | VAV Boxes & Controls | 165000 | 82500 | 49500 | 16500
5 | Rooftop Units (RTU) — 3 units | 310000 | 310000 | 0 | 0
6 | Chilled Water Piping | 142000 | 71000 | 42600 | 8520
7 | Hot Water Piping & Boiler Connections | 98000 | 49000 | 24500 | 0
8 | Plumbing — Rough-In | 136000 | 108800 | 20400 | 0
9 | Plumbing Fixtures & Trim | 74000 | 0 | 0 | 37000
10 | Fire Sprinkler System | 95000 | 47500 | 28500 | 0
11 | Building Automation System (BAS) | 112000 | 33600 | 22400 | 0
12 | Insulation — Duct & Pipe | 68000 | 34000 | 17000 | 0
13 | Testing, Adjusting & Balancing (TAB) | 45000 | 0 | 0 | 0
14 | Commissioning & Startup | 38000 | 0 | 0 | 0
15 | Approved Change Orders (CO #1-3) | 167500 | 58625 | 33500 | 0
GRAND TOTAL