## Dashboard
Apex Electrical Contractors -- Change Order Recovery Dashboard
As of 2026-04-09
KEY PERFORMANCE INDICATORS
Total CO Value Submitted | Total Approved | Total Pending | Total Rejected | Recovery Rate % | Avg Days to Approval | Revenue at Risk (Pending > 30d)
STATUS BREAKDOWN
Status | Count | Total Value | % of Total
Approved
Pending
Rejected
Withdrawn
TOTAL
BY PROJECT
Project | COs | Submitted | Approved | Recovery %
Mercy Hospital MRI Suite
Target Store #4412
Rivian Plant Phase 3
Data Center Build-Out
T&M SUMMARY
Total T&M Value
% Linked to COs
% with GC Signatures

## By Project
Apex Electrical Contractors -- Change Orders by Project
As of 2026-04-09
CO # | Project Name | Description | Date Submitted | Labor Cost | Material Cost | Markup | Total Submitted | Status | Date Approved | Amount Approved | Aging (Days) | Billing Status
CO-001 | Mercy Hospital MRI Suite | Added isolation transformer and dedicated 200A panel for MRI equipment per revised MEP drawings | 2026-01-15 | 18500 | 12800 |  |  | Approved | 2026-02-03 | 38200 |  | Billed
CO-002 | Mercy Hospital MRI Suite | Reroute conduit runs in ceiling plenum due to unforeseen HVAC ductwork conflict | 2026-02-10 | 6200 | 2100 |  |  | Approved | 2026-02-28 | 10375 |  | Collected
Mercy Hospital MRI Suite Subtotal
CO-003 | Target Store #4412 | Add 12 additional LED high-bay fixtures in stockroom per revised RCP | 2026-02-20 | 4800 | 7200 |  |  | Approved | 2026-03-10 | 15000 |  | Unbilled
CO-004 | Target Store #4412 | Upgrade 400A switchgear to accommodate additional EV charging stations | 2026-01-28 | 14200 | 28500 |  |  | Pending |  | 0 |  | Unbilled
Target Store #4412 Subtotal
CO-005 | Rivian Plant Phase 3 | Install temporary power distribution for early equipment commissioning | 2026-03-01 | 9800 | 5600 |  |  | Pending |  | 0 |  | Unbilled
CO-006 | Rivian Plant Phase 3 | Additional fire alarm devices per revised life safety drawings | 2026-02-05 | 22000 | 18500 |  |  | Pending |  | 0 |  | Unbilled
Rivian Plant Phase 3 Subtotal
CO-007 | Data Center Build-Out | Upgrade bus duct from 2000A to 3000A per revised single-line diagram | 2026-02-15 | 31000 | 45000 |  |  | Pending |  | 0 |  | Unbilled
CO-008 | Data Center Build-Out | Premium time for weekend work to meet accelerated schedule | 2026-03-15 | 8400 | 0 |  |  | Rejected |  | 0 |  | Unbilled
Data Center Build-Out Subtotal
GRAND TOTAL
Formulas:
Aging (Days) = IF([Status]="Approved",IF([Date Approved]="","",INT([Date Approved]-[Date Submitted])),IF([Date Submitted]="","",INT(TODAY()-[Date Submitted])))

## T&M Log
Apex Electrical Contractors -- T&M Log
As of 2026-04-09
Date | Project | Description | Labor Hours | Labor Cost | Material Cost | Equipment Cost | Total | GC Signature | Linked CO # | Status
2026-01-12 | Mercy Hospital MRI Suite | Isolation transformer installation - journeyman electrician x2 | 16 | 1520 | 4200 | 350 |  | Y | CO-001 | Linked
2026-01-14 | Mercy Hospital MRI Suite | 200A panel installation and circuit wiring | 24 | 2280 | 8600 | 0 |  | Y | CO-001 | Linked
2026-02-08 | Mercy Hospital MRI Suite | Conduit reroute around HVAC ductwork - foreman + 2 journeymen | 32 | 3400 | 2100 | 180 |  | Y | CO-002 | Linked
2026-02-18 | Target Store #4412 | LED high-bay fixture installation in stockroom | 20 | 1900 | 7200 | 450 |  | Y | CO-003 | Linked
2026-01-25 | Target Store #4412 | Switchgear upgrade demo and prep work | 12 | 1140 | 0 | 200 |  | Y | CO-004 | Linked
2026-02-28 | Rivian Plant Phase 3 | Temporary power panel installation | 8 | 760 | 1800 | 0 |  | Y | CO-005 | Linked
2026-02-03 | Rivian Plant Phase 3 | Fire alarm device rough-in - Phase 1 | 40 | 3800 | 6200 | 0 |  | Y | CO-006 | Linked
2026-02-10 | Rivian Plant Phase 3 | Fire alarm device rough-in - Phase 2 | 36 | 3420 | 4800 | 0 |  | N | CO-006 | Linked
2026-03-12 | Data Center Build-Out | Bus duct demo and measurement for upgrade | 16 | 1680 | 0 | 800 |  | Y | CO-007 | Linked
2026-03-14 | Data Center Build-Out | Weekend overtime - cable pulling and termination | 24 | 3360 | 0 | 0 |  | N | CO-008 | Linked
2026-03-20 | Rivian Plant Phase 3 | Emergency generator connection - unplanned | 8 | 1120 | 640 | 0 |  | N |  | Submitted
2026-04-01 | Data Center Build-Out | Additional grounding electrode installation | 12 | 1260 | 1800 | 150 |  | Y |  | Priced
2026-04-03 | Data Center Build-Out | UPS bypass switch relocation | 6 | 630 | 0 | 0 |  | N |  | Draft
2026-04-05 | Mercy Hospital MRI Suite | Nurse call system conduit stub-outs - added scope | 10 | 950 | 380 | 0 |  | N |  | Draft
TOTAL: 14 Tickets
SUMMARY
Total T&M Value
% Linked to COs
% with GC Signatures