## Dashboard
Douglas Electric
Manpower Loading Chart
Report Date: 2026-04-07
KEY METRICS
Total Headcount (Week 1)
Total Projects
Avg Utilization %
Over/Under-staffed Projects
PROJECT SUMMARY
Project Name | Status | Total Planned Hours | Total Actual Hours | Variance | Variance % | Health
Rivian Plant Phase 3 | Active |  | 4200
Mercy Hospital MRI Suite | Active |  | 1800
Target Store #4412 Remodel | Active |  | 960
Applebee's Service Call | Winding Down |  | 320
Data Center Build-Out | Mobilizing |  | 0
EV Charging Station - Walmart | Mobilizing |  | 0
TOTAL

## Loading Chart
Douglas Electric
Manpower Loading Chart
Report Date: 2026-04-07
Project | Class | 2026-04-06 | 2026-04-13 | 2026-04-20 | 2026-04-27 | 2026-05-04 | 2026-05-11 | 2026-05-18 | 2026-05-25 | 2026-06-01 | 2026-06-08 | 2026-06-15 | 2026-06-22
Rivian Plant Phase 3 | DE-2026-001
| JW | 8 | 8 | 10 | 10 | 12 | 12 | 12 | 14 | 14 | 14 | 12 | 10
| AP | 6 | 6 | 8 | 8 | 10 | 10 | 10 | 12 | 12 | 12 | 10 | 8
| FM | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2
Total
Mercy Hospital MRI Suite | DE-2026-002
| JW | 4 | 4 | 4 | 5 | 5 | 5 | 4 | 3 | 2 | 2 | 1 | 0
| AP | 3 | 3 | 4 | 4 | 4 | 4 | 3 | 2 | 2 | 1 | 1 | 0
| FM | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
Total
Target Store #4412 Remodel | DE-2026-003
| JW | 3 | 3 | 3 | 3 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0
| AP | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0
| FM | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total
Applebee's Service Call | DE-2026-004
| JW | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| AP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| FM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total
Data Center Build-Out | DE-2026-005
| JW | 0 | 0 | 2 | 4 | 6 | 8 | 10 | 10 | 12 | 12 | 14 | 14
| AP | 0 | 0 | 1 | 3 | 5 | 6 | 8 | 8 | 10 | 10 | 12 | 12
| FM | 0 | 0 | 1 | 1 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3
Total
EV Charging Station - Walmart | DE-2026-006
| JW | 0 | 0 | 0 | 0 | 2 | 3 | 3 | 3 | 3 | 3 | 2 | 2
| AP | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2
| FM | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Total
GRAND TOTAL
CLASSIFICATION SUMMARY
Journeyman | JW
Apprentice | AP
Foreman | FM
Grand Total
JW:AP Ratio

## Apprentice Ratio Monitor
Douglas Electric
Apprentice Ratio Monitor
Report Date: 2026-04-07
Project Name | JW Count | AP Count | JW:AP Ratio | Required Ratio | Compliant
Rivian Plant Phase 3 |  |  |  | 1
Mercy Hospital MRI Suite |  |  |  | 1
Target Store #4412 Remodel |  |  |  | 1
Applebee's Service Call |  |  |  | 1
Data Center Build-Out |  |  |  | 1
EV Charging Station - Walmart |  |  |  | 1
COMPLIANCE SUMMARY
Total Compliant
Total Non-Compliant
Compliance %